## Project Overview
Project Details
1 | Project Title | : | Commercial Boulevard of Lusail
2 | Project ref# | : | CBD123456LS
3 | Client | : | Qatar Diar - LREDC
4 | Start Date | : | 2022-12-01
5 | End Date | : | 2026-05-30
6 | Project Value | : | 83000000

## Financial
Month/Year | Budget vs, Actual Cost |  |  | Revenue & Profitability |  |  | Contract Variations & Change Orders |  | BOQ vs. Actual
| Budgeted Cost | Actual Cost (OPEX) | Cost Variance | Revenue & Profitability | Profit | Profit Margin (GP) | No. of Variations | Total Variation Impact (Cost) | BOQ (Planned Qty) | Actual Qty | BOQ Variance
2025-01-31 | 1619512.1951 | 1478033.3333 | -141478.8618 | 1850000 | 371966.6667 | 20.11% | 2 | 1500000 | 500 | 480 | -20
2025-02-28 | 1619512.1951 | 1128893.3333 | -490618.8618 | 1630000 | 501106.6667 | 30.74% | 1 | 500000 | 600 | 610 | 10
2025-03-31 | 1619512.1951 | 1393264.3333 | -226247.8618 | 1800000 | 406735.6667 | 22.6% | 55 | 5000000 | 550 | 560 | 10
2025-04-30 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
2025-05-31 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
2025-06-30 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
2025-07-31 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
2025-08-31 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
2025-09-30 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
2025-10-31 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
2025-11-30 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
2025-12-31 | 1619512.1951 | 0 | 0 |  | 0 | 0% |  |  |  |  | 0
TOTAL | 4858536.5854 | 4000191 | -858345.5854 | 5280000 | 1279809 | 24.24% | 58 | 7000000 | 1650 | 1650 | 0
Note: | Revenue & Profitability include certified and uncertified amount
Note on E2: Yahya Chaker: Only Approved Amount

## OPEX
SR# | Category | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | Year Total
1 | Labor Costs
1.1 | Direct Labor | 350000 | 332190 | 374553 | [9 empty] | 1056743
1.2 | Indirect Labor | 80000 | 58776 | 37042 | [9 empty] | 175818
1.3 | Subtotal Labor | 430000 | 85273 | 411595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 926868
2 | Materials & Consumables | 100000 | 85087 | 74929 | [9 empty] | 260016
3 | Equipment & Tools | 50000 | 60000 | 37907 | [9 empty] | 147907
4 | Subcontracted Services | 845033.3333 | 845533.3333 | 815833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2506400
5 | Utilities | 3000 | 3000 | 3000 | [9 empty] | 9000
6 | Overheads & Indirect Costs | 50000 | 50000 | 50000 | [9 empty] | 150000
7 | Other Variable Costs | 0 | [11 empty] | 0
8 | TOTAL OPEX (Actual) | 1478033.3333 | 1128893.3333 | 1393264.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000191

## KPI-Penalties
Month | KPI Score | Base Bill | KPI Deduction % | KPI Deduction | Penalty (Delayed WOs) | Net Invoice
2025-01-31 | 85% | 2024390.2439 | 1% | 20243.9024 | 5000 | 1999146.3415
2025-02-28 | 96% | 1724390.2439 | 0% | 0 | 10000 | 1714390.2439
2025-03-31 | 70% | 1924390.2439 | 4% | 76975.6098 | 3000 | 1844414.6341
2025-04-30 | [5 empty] | 0
2025-05-31 | [5 empty] | 0
2025-06-30 | [5 empty] | 0
2025-07-31 | [5 empty] | 0
2025-08-31 | [5 empty] | 0
2025-09-30 | [5 empty] | 0
2025-10-31 | [5 empty] | 0
2025-11-30 | [5 empty] | 0
2025-12-31 | [5 empty] | 0
Total | 83.67% | 5673170.7317 |  | 97219.5122 | 18000 | 5557951.2195

## Billing
Month | Status | Submitted Date | Submitted Amount | Certified Amount | disputed Amount | Received | Notes
2025-01-31 | Submitted | 2025-01-03 | 1999146.3415 | 1850000 | 149146.3415 | Yes
2025-02-28 | Under Client Review | 2025-02-05 | 1714390.2439 | 1630000 | 84390.2439 | No
2025-03-31 | Under preparation |  | 1844414.6341 | 1800000 | 44414.6341
2025-04-30 |  |  | 0 |  | 0
2025-05-31 |  |  | 0 |  | 0
2025-06-30 |  |  | 0 |  | 0
2025-07-31 |  |  | 0 |  | 0
2025-08-31 |  |  | 0 |  | 0
2025-09-30 |  |  | 0 |  | 0
2025-10-31 |  |  | 0 |  | 0
2025-11-30 |  |  | 0 |  | 0
2025-12-31 |  |  | 0 |  | 0
TOTAL |  |  | 5557951.2195 | 5280000 | 277951.2195

## Manpower
SR# | Trade / Role | Reporting To | Levels | BOQ | Actual as of
[5 empty] | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31
1 | FM Manager |  | 1 | 1 | bar: 2025-01-31 to 2025-03-31
2 | Electrical Engineer | FM Manager | 2 | 1 | bar: 2025-01-31 to 2025-03-31
3 | Mechanical Engineer | FM Manager | 2 | 1 | bar: 2025-01-31 to 2025-03-31
4 | HVAC Engineer | FM Manager | 2 | 1 | 2025-01-31: 1; 2025-02-28: 0; 2025-03-31: 0
5 | ELV Engineer | FM Manager | 2 | 1 | bar: 2025-01-31 to 2025-03-31
6 | MEP Supervisor | Mechanical Engineer | 3 | 4 | 2025-01-31: 5; 2025-02-28: 4; 2025-03-31: 3
7 | ELV technician | MEP Supervisor | 4 | 1 | 2025-01-31: 1; 2025-02-28: 0; 2025-03-31: 0
8 | Electrician | MEP Supervisor | 4 | 10 | 2025-01-31: 8; 2025-02-28: 9; 2025-03-31: 10
9 | Plumber | MEP Supervisor | 4 | 10 | 2025-01-31: 10; 2025-02-28: 8; 2025-03-31: 9
10 | HVAC | MEP Supervisor | 4 | 10 | 2025-01-31: 10; 2025-02-28: 10; 2025-03-31: 9
11 | Helper | MEP Supervisor | 5 | 20 | 2025-01-31: 20; 2025-02-28: 20; 2025-03-31: 20
12 | Security Supervisor | FM Manager | 3 | 2 | 2025-01-31: 2; 2025-02-28: 2; 2025-03-31: 2
13 | Security | Security Supervisor | 4 | 50 | 2025-01-31: 46; 2025-02-28: 48; 2025-03-31: 50
14 | Cleaning Supervisor | FM Manager | 3 | 4 | 2025-01-31: 4; 2025-02-28: 5; 2025-03-31: 4
15 | Cleaner | Security Supervisor | 4 | 50 | 2025-01-31: 47; 2025-02-28: 45; 2025-03-31: 50
| Teaboy | Cleaning Supervisor | 5 | 0 | 2025-01-31: 3; 2025-02-28: 3; 2025-03-31: 3
| Total |  |  | 166 | 158 | 155 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SLA Compliance
Service Level Agreement (SLA) Compliance
Month | SLA # | SLA Name | Target % | Measured Value % | Compliance Status | Remarks
2025-01-01 | SLA-01 | Response Time | 90% | 88% | Not Met | Work overload in Jan
| SLA-02 | Uptime | 99% | 99.5% | Met
| SLA-03 | Safety Audit | 100% | 100% | Met
2025-02-01 | SLA-01 | Response Time | 90% | 91% | Met | Improved staff levels
| SLA-02 | Uptime | 99% | 95% | Not Met
| SLA-03 | Safety Audit | 100% | 93% | Not Met
2025-03-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-04-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-05-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-06-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-07-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-08-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-09-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-10-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-11-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%
2025-12-01 | SLA-01 | Response Time | 90%
| SLA-02 | Uptime | 99%
| SLA-03 | Safety Audit | 100%

## PPM
Planned vs. Completed Progress (PPM)
Month | Planned Tasks | Completed Tasks | % Completion | Carry-Over from Previous | Target | Notes/Remarks
2025-01-31 | 3500 | 3300 | 94.29% | 200 | Below Target | Any special reasons, etc.
2025-02-28 | 3700 | 3650 | 98.65% | 50 | Above Target | ...
2025-03-31 | 3300 | 3000 | 90.91% | 300 | Below Target | ...
2025-04-30 |  |  | 0% | 0
2025-05-31 |  |  | 0% | 0
2025-06-30 |  |  | 0% | 0
2025-07-31 |  |  | 0% | 0
2025-08-31 |  |  | 0% | 0
2025-09-30 |  |  | 0% | 0
2025-10-31 |  |  | 0% | 0
2025-11-30 |  |  | 0% | 0
2025-12-31 |  |  | 0% | 0

## WOs
Raised WOs vs. Work Order Completion Rate
Month | WOs Raised | WOs Completed | Completion Rate | Backlog (Open WOs)
2025-01-31 | 50 | 45 | 90% | 5
2025-02-28 | 40 | 38 | 95% | 7
2025-03-31 | 60 | 55 | 91.67% | 12
2025-04-30 |  |  | 0% | 12
2025-05-31 |  |  | 0% | 12
2025-06-30 |  |  | 0% | 12
2025-07-31 |  |  | 0% | 12
2025-08-31 |  |  | 0% | 12
2025-09-30 |  |  | 0% | 12
2025-10-31 |  |  | 0% | 12
2025-11-30 |  |  | 0% | 12
2025-12-31 |  |  | 0% | 12
Total | 150 | 138 | 92% | 12

## Services
Services
SR# | Systems included in SOW | Ownership | Subcontractor Detail | Status | Start Date | End Date | Contract Value
1 | System 1 | In-House |  | Active | 2023-01-01 | 2026-05-30
2 | System 2 | In-House |  | Active | 2023-01-01 | 2026-05-30
3 | System 3 | In-House |  | Active | 2023-01-01 | 2026-05-30
4 | System 4 | In-House |  | Active | 2023-01-01 | 2026-05-30
5 | System 5 | In-House |  | Active | 2023-01-01 | 2026-05-30
6 | System 6 | In-House |  | Active | 2023-01-01 | 2026-05-30
7 | System 7 | In-House |  | On Hold | 2023-01-01 | 2026-05-30
8 | System 8 | Subcontractor | Subcon-01 | Active | 2024-05-01 | 2026-05-30 | 1500000
9 | System 9 | Subcontractor | Subcon-02 | Active | 2024-05-02 | 2026-05-30 | 3000000
10 | System 10 | Subcontractor | Subcon-03 | Active | 2024-05-03 | 2026-05-30 | 5000000
11 | System 11 | Subcontractor | Subcon-04 | Active | 2024-05-04 | 2026-05-30 | 2000000
12 | System 12 | Subcontractor | Subcon-05 | Active | 2024-05-05 | 2026-05-30 | 7000000
13 | System 13 | Subcontractor | Subcon-06 | Active | 2024-05-06 | 2026-05-30 | 1800000
14 | System 14 | Subcontractor |  | Not Started
15 | System 15 | Subcontractor |  | Not Started
| Total | [5 empty] | 20300000

## Subcontractors
Subcontractors
System Description | System 8 | System 9 | System 10 | System 11 | System 12 | System 13 | System 14 | System 15 | Total
Subcon Name | Subcon-01 | Subcon-02 | Subcon-03 | Subcon-04 | Subcon-05 | Subcon-06 | 0 | 0
Total Budgeted Vlaue | 1300000 | 3200000 | 6000000 | 1800000 | 7800000 | 2200000 |  |  | 22300000
Total Contract Value | 1500000 | 3000000 | 5000000 | 2000000 | 7000000 | 1800000 | 0 | 0 | 20300000
Strat Date | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06
End Date | 2026-05-30 | 2026-05-30 | 2026-05-30 | 2026-05-30 | 2026-05-30 | 2026-05-30
Contract Duration | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0
Monthly Billing | 62500 | 125000 | 208333.3333 | 83333.3333 | 291666.6667 | 75000 | 0 | 0 | 845833.3333

## Subcontractor Monthly Billing
Subcontractor Monthly Billing Submittal
Month | Bill Details | Value | [7 empty] | Total
2025-01-01 | Base Invoice | 62500 | 125000 | 208333.3333 | 83333.3333 | 291666.6667 | 75000 | 0 | 0 | 845833.3333
| KPI / Deduction | -500 | -300 | [6 empty] | -800
2025-02-01 | Base Invoice | 62500 | 125000 | 208333.3333 | 83333.3333 | 291666.6667 | 75000 | 0 | 0 | 845833.3333
| KPI / Deduction | 0 | -300 | [6 empty] | -300
2025-03-01 | Base Invoice | 62500 | 125000 | 208333.3333 | 83333.3333 | 291666.6667 | 75000 |  |  | 845833.3333
| KPI / Deduction | -5000 | -10000 | -15000 | [5 empty] | -30000
2025-04-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
2025-05-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
2025-06-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
2025-07-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
2025-08-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
2025-09-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
2025-10-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
2025-11-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
2025-12-01 | Base Invoice | [8 empty] | 0
| KPI / Deduction | [8 empty] | 0
Total Subcon | 2506400 | 182000 | 364400 | 610000 | 250000 | 875000 | 225000 | 0 | 0 | 2506400
*if no amount is added then no invoice is received